## Submittal Log Template
(Sample) MATERIAL SUBMITTAL LOG TEMPLATE
Project Name
Project ID
Prime Contractor
Project Manager
Engineer
Spec Section # | Section Name | Sub Spec Section | Description | Submittal Type | Priority | Approval Status | Submittal Contractor | Project Manager | Reviewer | Co-Reviewers | Required Date | Required Approval Date | Lead Time (Days) | Notes
11-100 | Concrete Waterproofing Coating | 3.05-A | Submit manufacturers literature and technical data describing coating | Product Data | HIGH | OPEN | Name: Company: Email: | Name: Company: Email: | Name: Company: Email: | Name: Company: Email:
12-150 | Exterior Metal Cladding Wall System | 4.05-B | Submit scaled shop drawings prepared specifically for Project to illustrate details, dimensions, and other performance data necessary to fully describe fabrication and installation of wall system | Shop Drawings | NORMAL | APPROVED | Name: Company: Email: | Name: Company: Email: | Name: Company: Email: | Name: Company: Email: | 2021-02-21 | 2021-03-26 | 90
A documented material submittal process is critical to ensuring construction materials meet original design specifications. This is especially true for waterproofing and weather related building components. A log also documents architect and engineer approvals and provides documentation to aide in the defense of any future construction defect claims.
The information presented here is intended to help users address their own risk management and insurance needs. It does not and is not intended to provide legal advice. Nationwide, its affiliates and employees do not guarantee improved results based upon the information contained herein and assume no liability in connection with the information or the provided suggestions. The recommendations provided are general in nature; unique circumstances may not warrant or require implementation of some or all of the suggestions. Nothing here is intended to imply a grant of coverage. Each claim will be evaluated on its own merits and circumstances. Nationwide, Nationwide is on your side, and the Nationwide N and Eagle are service marks of Nationwide Mutual Insurance Company. © 2021 Nationwide